## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | User Authentication with JWT (Signup, Login) | Must Have |  | Harsha | Completed
Sprint 1 | Sprint 1 | US002 | Ticket Submission & DB Schema (PostgreSQL) | Must Have | US001 | Harsha | Completed
Sprint 2 | Sprint 2 | US003 | AI Prediction: Category & Priority (TF‑IDF + SGD) | Must Have | US002 | Harsha | Completed
Sprint 2 | Sprint 2 | US004 | Professional Dashboard UI (Tailwind) | Must Have |  | Harsha | Completed
Sprint 3 | Sprint 3 | US005 | Manager Hub: Global Tickets & Stats | Must Have | US003 | Harsha | Completed
Sprint 3 | Sprint 3 | US006 | Review & Rating System | Should Have | US002 | Harsha | Completed
Sprint 4 | Sprint 4 | US007 | Admin APIs: Users, Stats, Role-based Access | Must Have | US005 | Harsha | Completed
Sprint 4 | Sprint 4 | US008 | CORS/Deployment Hardening & Health Probes | Must Have |  | Harsha | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate | Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US001 | T01-01 | Design DB schema & user table | 2026-01-01 | 2026-01-02 | Harsha | Dev | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T01-02 | Implement Signup endpoint | 2026-01-02 | 2026-01-03 | Harsha | Dev | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T01-03 | Implement Login & JWT | 2026-01-03 | 2026-01-04 | Harsha | Dev | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | T01-04 | Ticket model & CRUD | 2026-01-04 | 2026-01-05 | Harsha | Dev | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | T01-05 | Connect Supabase/Postgres | 2026-01-05 | 2026-01-06 | Harsha | Dev | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US003 | T02-01 | Build TF‑IDF pipeline | 2026-01-15 | 2026-01-16 | harsha | ML | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US003 | T02-02 | Train SGD grid search | 2026-01-16 | 2026-01-17 | Harsha | ML | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US004 | T02-03 | Design dashboard layout | 2026-01-17 | 2026-01-18 | Harsha | UI/UX | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US004 | T02-04 | Implement SPA navigation | 2026-01-18 | 2026-01-19 | Harsha | Frontend | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | T03-01 | Admin endpoints: users, tickets | 2026-01-29 | 2026-01-30 | Harsha | Backend | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | T03-02 | Owner name join for admin | 2026-01-30 | 2026-01-31 | Harsha | Backend | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US006 | T03-03 | Rating modal/UI | 2026-01-31 | 2026-02-01 | Harsha | Frontend | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US006 | T03-04 | Review API & metrics | 2026-02-01 | 2026-02-02 | Harsha | Backend | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US007 | T04-01 | Manager stats API | 2026-02-12 | 2026-02-13 | Harsha | Backend | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US007 | T04-02 | Manager Hub UI table | 2026-02-13 | 2026-02-14 | Harsha | Frontend | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US008 | T04-03 | CORS allowlist & health check | 2026-02-14 | 2026-02-15 | Harsha | DevOps | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US008 | T04-04 | Render deployment tuning | 2026-02-15 | 2026-02-16 | Harsha | DevOps | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Environment setup delays | Pinned Python, installed deps
Sprint 1 | Day 7 | Model accuracy for Billing | Added bigrams, tuned params
Sprint 1 | Day 14 | CORS conflicts in prod | Explicit allowlist & tests
Sprint 2 | Day 1 | Environment setup delays | Pinned Python, installed deps
Sprint 2 | Day 7 | Model accuracy for Billing | Added bigrams, tuned params
Sprint 2 | Day 14 | CORS conflicts in prod | Explicit allowlist & tests
Sprint 3 | Day 1 | Environment setup delays | Pinned Python, installed deps
Sprint 3 | Day 7 | Model accuracy for Billing | Added bigrams, tuned params
Sprint 3 | Day 14 | CORS conflicts in prod | Explicit allowlist & tests
Sprint 4 | Day 1 | Environment setup delays | Pinned Python, installed deps
Sprint 4 | Day 7 | Model accuracy for Billing | Added bigrams, tuned params
Sprint 4 | Day 14 | CORS conflicts in prod | Explicit allowlist & tests

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-01 | 2026-01-14 | Harsha | Automate migrations; add CI checks | Hardcoding origins; manual DB scripts | Daily reviews; small PRs | Stabilized core features
2 | Sprint 2 | 2026-01-15 | 2026-01-28 | Harsha | Automate migrations; add CI checks | Hardcoding origins; manual DB scripts | Daily reviews; small PRs | Stabilized core features
3 | Sprint 3 | 2026-01-29 | 2026-02-11 | Harsha | Automate migrations; add CI checks | Hardcoding origins; manual DB scripts | Daily reviews; small PRs | Implemented Manager Hub and metrics
4 | Sprint 4 | 2026-02-12 | 2026-02-25 | Harsha | Automate migrations; add CI checks | Hardcoding origins; manual DB scripts | Daily reviews; small PRs | Implemented Manager Hub and metrics